## Sheet1
Indicative project timeline | Primary Undertaking / Consent Outline | Administering body (who signs / issues) | Typical submission contents | Construction milestone it unlocks
1 Pre-application engagement | EIA/EOR scoping, design-code discussion, Planning-Performance Agreement | Local Planning Authority (Scotland: Planning Authority) – Development-Management team; statutory consultees (EA / SEPA, highway, LLFA, etc.) give informal views | Draft constraints plan, CSM, traffic scoping | Land deal, baseline surveys start
2 Outline Planning Permission / PPiP decision | Decision notice with conditions & s106/s75 heads | Local Planning Authority / Planning Authority (planning committee or delegated officer) | Land-use parameters, max units, access points, draft phasing | Green light for detailed design; still no physical works
3 Early pre-commencement condition discharge | Phase-1 PRA, archaeology WSI, CEMP | Local Planning Authority – condition-discharge officer; consultees (Environmental Health, County Archaeologist, Ecology) advise | Desk study, trenching plan, ecological method statements | Site clearance, invasive-species removal, GI boreholes
4 RM / MSC Package 1 – Infrastructure masterplan | Roads & levels, drainage/SuDS strategy, landscape framework, phasing plan | Local Planning Authority / Planning Authority | Roads & levels, drainage/SuDS strategy, landscape framework, phasing plan | Bulk earthworks, strategic drainage, compound set-up
5 Technical consents for infrastructure• RCC (Scot.) or s38 / s278 (Eng/Wales)• s104 sewer adoption (Eng/Wales) / Sewers for Scotland vesting |  | • Local Roads Authority (Scot.) / Local Highway Authority (Eng/Wales) – plus National Highways / Transport Scotland if trunk road• Statutory Sewerage Undertaker (e.g. Scottish Water, Thames Water) | Detailed road drawings & sections, swept-paths, pavement make-up; sewer long-sections, flow calcs | Spine roads, foul & surface-water networks, utilities corridors
6 RM / MSC Package 2 – Plots & housing detail | House-type drawings, materials, FFLs, boundaries | Local Planning Authority / Planning Authority | House-type drawings, materials, FFLs, boundaries | Plot foundations, superstructure
7 Non-material variations / s64 (Scot.) or s73 (Eng/Wales) | Fenestration tweaks, brick swaps, sub-station moves | Local Planning Authority / Planning Authority | Variation statements, updated drawings | Keeps live plots lawful while building
8 During-construction condition discharge | Tree-protection, noise bund, energy, open-space layouts | Local Planning Authority (often the same officer as at stage 3) | Drawings, specs, method statements | First-fix trades, show-home opening
9 Pre-occupation discharge & verifications | Phase-4 CL verification, SuDS maintenance plan, Travel Plan | Local Planning Authority / Planning Authority (with sign-off from Environmental Health; Scotland: Building Standards) | Lab certs, as-built drawings, gas-membrane test, SuDS O&M plan | Building-Control completion, first handovers
10 Adoptions & close-out | Road adoption certificate, sewer vesting, bond release | • Roads / Highway Authority (same body that issued RCC / s38)• Sewerage Undertaker• Local Planning Authority for any final conditions | Final inspection sheets, CCTV of sewers, maintenance schedules | End of defect liability; site compound removed